## Slide 1: Building country specific Omnichannel HCP Journeys to support launch
April 2021

## Slide 2: HCP Journeys Project
Jyseleca currently has a foundation of strategic planning related to customer engagement activities for launch, including detailed segmentation and market research.
A core team with the support of Veeva, are now focused on making the plan a reality, by converting these foundations into HCP Journeys that are practical and actionable at the local level to secure competitive share of voice and achieve a successful launch.

## Slide 3: Journey Mapping enables the visualisation of a target HCP experience
Uncover behavioral segments by analyzing HCP data across touchpoints over time
Measure the impact of HCP behavior on KPIs
Ideate and communicate journeys for Jyseleca to become more HCP centric
Create a visualization of your HCP experience across touchpoints over time, including actions and emotions as they seek to treat their RA patients
Increase the rate and speed at which HCPs complete their own unique and semi-personalized journey to reach an objective
Create and use a platform to create and test hypothesis to learn how to interact most efficiently with each HCP based on their unique journey
A deeper understanding of HCP needs, behaviors, emotions as they seek to achieve a goal
A journey dashboard to bring together qualitative and quantitative data to highlight factors with greatest impact on goal achievement
t
01
02
03
04
05
Journey discovery
Journey Mapping
HCP Journey Capabilities
Journey Orchestration
Journey Optimization
Journey Insights
HCP Journey capabilities
Project Scope
Coordinate interactions across channels, automate interactions (where possible and relevant) at each step of journey
Personalize engagement using information about HCP and where they are in the journey
Build a platform that automates real time personalized interactions to improve journey flow and drive desirable outcomes for HCPs and patients

## Slide 4: The international team would like to support you in developing omnichannel customer journeys for your market
We are starting a rapid, focused project to co-create pragmatic, executable, local Customer Journeys that will help drive superior HCP experiences
International Journeys delivered by end of April
Detailed market Journeys to be delivered by end of May
*Country-specific - See project plan for detailed schedule

## Slide 5: What will you get at the end?
A clear, 12-month* Customer Journey for your market, specific to RA indication, linked to driving HCPs up the initial stages in the adoption ladder
Journeys that are linked to content both existing and currently in production for launch, with easy access to the materials needed for execution (and view on planned content)
An easy-to-use Customer Journey format, to enable dynamic updates throughout the year
*length is an estimate, journeys will likely be more focused around adoption stage TBD during week 1
**See project plan for market and indication delivery details

## Slide 6: Your support throughout this process is essential to ensure the journeys we create together help drive your local campaign execution

## Slide 7: How do we get there: The Principles
Simple
The Journeys will be as simple as possible, and not overcomplicated to ensure easy execution (e.g. applicable in your daily work)
Practical
The Journeys will be connected to existing and future content, and aligned to key events
Local
After creating an international version, we will work with you to localise the journeys to meet your market need
We want to ensure these journeys are actionable for your market, so we have three core principles

## Slide 8: How do we get there: The Process
Adoption Ladder
HCP Journeys
The HCP-focused mapping of the level of product adoption.
The execution-focused mapping of the touchpoints with a HCP.
1
2

## Slide 9
#1
#2
#3
#4
#5
CURRENT
DESIRED
Tries JYSELECA with some patients
(After they have gained experience) Expand JYSELECA use in a wider range of patients in preference to other JAKs
Uses a very broad spectrum of products including JAKs
Uses very recently launched products
Able to talk extensively about new and pipeline treatments
Willing to act ahead of guidelines
Behaviour Change
Adoption Stage
Unmet Need
Research
1st Rx
Prescribes
Advocates
Galapagos Goal
Barriers
High-Level Goal
To demonstrate that despite new treatments, unmet needs still remain, especially related to a balance of efficacy and safety
Segmented Goals
Mavericks: Uses a wide variety of treatments 1st line, including JAKs
Pragmatists: Occasionally uses JAKs but not consistently [high variation within segment – some are very high JAK users]
Compassionates: Uses a variety of products based on patient need & guideline recommendations
Currently Unsegmented Barriers
Satisfied with current options
Complacency/habit
Don’t believe there are significant unmet needs that can be addressed by (another) JAK
Believe another MOA will be needed to address unmet needs
Communication gap between patients and HCPs that masks unmet needs/treatment gaps (especially Compassionates)
CoVid context : access challenge to care
Highly competitive environment with comparisons between treatments hard to make.
Treatment inertia and need to overcome mindset shift
High-Level Goal
To ensure early positive experiences as proof of concept (and to share with peers)
Segmented Goals
Mavericks: Reflects on early JYSELECA experience & positive efficacy outcomes compared with other JAKs
Pragmatists: Attends a peer-to peer discussion with local colleagues about their experiences with JYSELECA & its safety profile
Compassionates: Attends a discussion with local expert about their experiences with JYSELECA & its safety profile
Currently Unsegmented Barriers
Awareness & Access
Access to JYSELECA
Lack of access to sampling
Lack of experience with JYSELECA
Lack of familiarity with Galapagos and new relationship with reps
Differentiation
Perceived lack of differentiation from RINVOQ
Sees no difference in clinic relative to RINVOQ
Negative Safety Halo
Residual JAK concerns from 1st generation
Clinical
Has a negative experience in a patient in first few patients
Lack of clarity of who the ideal JYSELECA patient is
High-Level Goal
To differentiate JYSELECA versus other JAKs, especially RINVOQ
Segmented Goals
Mavericks: Prescribes JYSELECA as their ‘go to’ JAK
Pragmatists: Prescribes JYSELECA for some patients where safety is the main concern
Compassionates: Prescribes JYSELECA for some patients where safety & simplicity are important
Currently Unsegmented Barriers
Satisfaction with their current JAK and no reason to change
Prefer to have a wide armamentarium, rather than a go-to
Like to keep options open as new entries emerge
Competitive messaging and share of voice
Uncertainty around available JYSELELCA support services for HCPs and patients
Unsure of which patient population to expand usage in
High-Level Goal
To create an environment that facilitates exchange of positive experiences
Segmented Goals
Mavericks: Shares positive experiences with colleagues
Pragmatists: Gains depth of experience in patients where safety is a concern
Compassionates: Monitors feedback & safety signals in JYSELECA patients
Currently Unsegmented Barriers
Negative experiences that temper their enthusiasm
Wanting to appear unbiased/unaligned with a brand
High-Level Goal
To identify, support, and create a platform for JYSELECA advocates
Segmented Goals
Mavericks: Advocates JYSELECA as JAK of choice
Pragmatists: Expands the use of JYSELECA to different types of patients so ultimately JYSELECA becomes JAK of choice
Compassionates: Starts to use JYSELECA as first line JAK inhibitor
Currently Unsegmented Barriers
Do not have a JAK of choice and philosophically opposed to aligning with one product
Don’t have a platform from which to advocate
1
2
3
1
1
2
3
1
2
3
2
3
1
2
3
1
Notes: #1
Mavericks lowest priority as they will already try new things on their own.
Pragmatists are using JAKs so we need to demonstrate that there is still a need for a new/different JAKi
#2
Mavericks are most likely be early adopters and also share their experience so we want to ensure they have early positive experience
Pragmatists tend to bend the rules to solve problems, focusing on safety provides a strong reason to believe
Compassionates will want to hear from and be reassured by peers so important to get the other two comfortable first
#3
Pragmatists most concerned with safety – need to differentiate on safety to achieve earlier us and differentiate against RINVOQ
Mavericks third because they will try anyway and also form their own opinion
#4 and #5
Pragmatists first because they are more likely to be long-term advocates
Mavericks second because want to keep them interested in JYSELECA by giving them a platform but they may move on to other products
Compassionates last because they will wait to hear from M and P – so we need M and P on board and sharing their stories

## Slide 10
#1
#2
#3
#4
#5
CURRENT
DESIRED
Tries JYSELECA with some patients
(After they have gained experience) Expand JYSELECA use in a wider range of patients in preference to other JAKs
Uses a very broad spectrum of products including JAKs
Uses very recently launched products
Able to talk extensively about new and pipeline treatments
Willing to act ahead of guidelines
Behaviour Change
Adoption Stage
Unmet Need
Research
1st Rx
Prescribes
Advocates
Messages
Message Source
Message Objective by Segment:
Mavericks: significant need for new treatment options – they already agree with this and are keen to try new options, esp if efficacy is not compromised
Pragmatists: need for more safe treatment options that do not compromise on efficacy
Compassionates: focus on unmet needs from a patient perspective – less from an HCP perspective
Message Topics:
Unmet needs messaging : 1/3 patients are refractory, EULAR guidelines, (5messages in total)
FAQ on CoVid impact
Please refer to Brand Content Asset Overview
Message Objective by Segment:
Mavericks: expose to full data esp efficacy, give opportunity to try – make it easy, but they will be interested
Pragmatists: expose to full data incl safety, ref trusted peers/colleagues and hands on experience
Compassionates: KOL/Peer/trusted source perspectives on JYS safety and simplicity – ‘permission to try’
Message Topics
Now available
MoA : selectivity (vs 1G)
Comprehensive clinical evidence : 3 CT and long term data
Strength of balance story : full strength with safety)
Reimbursement : (to be localised)
Patient identification
HCP and Patient Support Service (Cpst) / to be localised)
Please refer to Brand Content Asset Overview
Message Objective by Segment:
Mavericks: reinforce experience, share additional data freely, seed need to share with others
Pragmatists: advocate trial and follow up re experience and expansion of trial use
Compassionates: share/encourage patient feedback, patient perspectives, PIO
Message Topics
Efficacy
Safety
Patient Profiles
Patient identification
Corporate support
HCP and Patient Support Service
Please refer to Brand Content Asset Overview
Message Objective by Segment:
Mavericks: provide opportunities to share experience and discuss with others
Pragmatists: expand patient types as experience is gained – give different ‘pegs
Compassionates: Monitors feedback & safety signals in JYSELECA patients
Message Topics
Efficacy
Safety
Patient Profiles
Patient identification
Corporate support
HCP and Patient Support Service
Please refer to Brand Content Asset Overview
Message Objective by Segment:
Mavericks: KOL opportunities – keeping in mind loyalty can prob not be expected
Pragmatists: consolidate experience to lead to JAK of choice ‘peg’]
Compassionates: consolidate experience and ptn feedback to lead to JAK of choice ‘peg’ and 1L use
Message Topics
Corporate support
HCP and Patient Support Service
Partnership opportunities
Please refer to Brand Content Asset Overview
1

## Slide 11: Brand Content Asset catalogue sorted by HCP segment will be provided to you
Extract

## Slide 12: We will use Custellence® to build the journeys
After comparing a multitude of tools, we believe Custellence has the best balance of features vs simplicity, with simplicity being key.
Custellence® is a simple, 1-page journey creation tool, with collaboration functionality.
We are using Custellence ® solely to help guide the creation of HCP Journeys, not for use in the orchestration or execution of journeys.

## Slide 13: How do we get there: The HCP Journey Map
2
DRAFT
Structured by Adoption Ladder Stage
Entry Point Scenarios
Different entry-points (e.g. Existing Relationship, Digital-only) necessitate specified journeys
Content Boxes
Each box represents assets, selected and organized with the goal of moving an HCP up the adoption ladder.

## Slide 14: The project plan detail
Today
Phase 1a
Customer Journey Foundations
March |  |  | April | April |  |  | May | May |  | 
15 | 22st (1) | 29th (2) | 5th (3) | 12th (4) | 19th (5) | 26th (6) | 3rd (7) | 10th (8) | 17th (9) | 24th (10)
Phase 1c
Detailed localization of RA/IBD Customer Journeys for large countries
Phase 1d
Localisation for smaller markets
Phase 1b
Build & Test international RA/IBD Customer Journey
Core project team
Core Team + International project team
Core Team
+
International project team +
2 Market Representatives
Journey Templates & Framework
Draft Adoption Pathways & Customer Journeys
Populated International Adoption Journey + International Customer Journeys
Local Adoption Journeys & Customer Journeys
+
Training & eLearning module
Team
Outputs
Format
We will be facilitating multiple workshops within your countries
to support the development of your local CJ
Countries: 2-3x two-hour workshops,
Working sessions
4 x 2-hour sessions
Working sessions
IBD  2 x 2-hour sessions
RA  2 x 2-hour sessions
UK (RA&IBD)
Germany (RA&IBD)
Spain (RA)
Italy (RA)
BelLux
NL
France (RA)
Market Introduction Meeting
Scheduled Market Workshop

## Slide 15: Engagement with a FR/UK/DE/ES/IT
Workshop 1
Workshop 2
Workshop 3
Who: (proposed)
The core team + Local team
Local team to include the required stakeholders to ensure accurate Journey development (Marketing / Medical / Sales)
Input:
International Adoption ladder
International Customer Journey
Local events calendar and content plans and prior work
Activity:
Working session to localise the global adoption ladder, and to localise the international HCP journey against key market events, channels and goals
Output:
Adoption Journey finalised
Draft of local HCP journey created leveraging potential existing work
Who: (proposed)
The core team + Local team
Local team to include the required stakeholders to ensure accurate Journey development (Marketing / Medical / Sales)
Input:
Local adoption ladder
Iteration #1 on HCP Journey
Activity:
Working session to iterate the local HCP journeys
Output:
Updated version of the local HCP journey
Who: (proposed)
The core team + Local team
Local team to include the required stakeholders to ensure accurate Journey development (Marketing / Medical / Sales)
Input:
Local adoption ladder
Iteration #2 HCP Journey
Activity:
Working session to finalise the local HCP journeys
Output:
Final version of the local HCP journey
2hrs
2hrs
2hrs
For UK & Germany, where both RA & IBD journeys are being created, the workshops will be run in parallel in separate groups for each indication, with the outputs being entirely specific.

## Slide 16: Engagement with a NL/BNL
Workshop 1
Workshop 2
Who: (proposed)
The core team + Local team
Local team to include the required stakeholders to ensure accurate Journey development (Marketing / Medical / Sales)
Input:
International adoption ladder
International HCP journey
Local events calendar and content plans
Journeys produced in 2020
Activity:
Working session to localise the global adoption ladder, and localising the international HCP journey against key market events, channels and goals
Output:
Adoption Journey finalised
Updated local HCP journey created
2hrs
2hrs
Week 1
Week 2
Who: (proposed)
The core team + Local team
Local team to include the required stakeholders to ensure accurate Journey development (Marketing / Medical / Sales)
Input:
Local adoption ladder
Workshop 2 HCP journey
Activity:
Working session to finalise the local HCP journeys
Output:
Final version of the local HCP journey

## Slide 17: Appendix

## Slide 18: Project Phases
March |  |  | April | April |  |  | May | May |  | 
15 | 22st (1) | 29th (2) | 5th (3) | 12th (4) | 19th (5) | 26th (6) | 3rd (7) | 10th (8) | 17th (9) | 24th (10)
Mobilization
Phase 1a
Foundations for HCP J Maps
Phase 1c
Detailed Localization of HJ Maps for France, Germany, UK, Spain, Italy
Phase 1d
Finalized Localization of HJ for NL and BelLux
Phase 1b
Build & Test Regional HJ Maps
Phase 2a
Define Alignment between CJ Maps & CRM/CDP
Phase 2b
Build action plan to operationalize alignment
Create Customer journey maps
Align maps with CRM/CDP
Build HCP journey map understanding
1
2
3
Project Management
Phase 3a
Build Tactic Plan
Phase 3b
Build e-learning module
Phase 3c
Train the Trainer (CJ Market Champions)

## Slide 19: An experienced Veeva team will helps us achieve our goals and will be supporting you
Brings deep LS Expertise and 8+ years defining Commercial Strategy and Operating Models
Louisa has worked with large enterprise Pharma in defining and executing on Commercial and Medical models including omni-channel orchestration and go to market engagement models.
Prior to joining Veeva she worked at EY and Accenture consulting where she worked in the US and Europe on complex multi geography / functional LS teams. Clients include Astellas, AZ, BMS, Takeda, Merck.
Louisa Peacock
Veeva Lead
SME
Aaron Bean
VP, Business Consulting Lead
Europe BC Head
Aaron leads Veeva's European Business Consulting Practice and specializes in commercial excellence, innovation and digital transformation. enabling clients to design and deliver world class customer experiences
He brings over 18+ years' experience, prior to Veeva, Aaron was the Life Sciences Advisory Lead in EY UK.
Brings expertise in designing Customer journeys with Galapagos France
Alexandre Leads Veeva's Business Consulting Practice in France and specialises in commercial excellence, innovation and digital transformation.
He brings 15 years' experience in marketing and sales functions both at affiliate and global level, working across the drug lifecycle and 7 therapeutic areas, including at Lilly.
Alexandre Raynaud
CJ Architect
Alex Richwood
Business Consultant
Gareth Allot
Engagement Manager
Brings extensive experience designing and operationalizing Commercial Models
Gareth has deep experience in the execution of omni-channel and leads on engagements across Europe in Field Force optimization and Veeva Pulse. being passionate about providing data driven insights.
Prior to joining Veeva Gareth worked in Accenture consulting’s HLS practice, leading multi market global commercial programs
Brings Field Force sizing, modelling and analytic capability
Alex has joined Veeva having recently completed an MBA at HEC Paris.
He has supported projects in sales force efficiency and optimization, providing market research, data and analytics.
Alex joined Veeva to help define and enable the new model for the future in LS.
CORE DELIVERY TEAM