## Workshop Calendar
Galapagos HCP Journeys - Detailed Workshop / Engagement Calendar
 | time axis 2021-03-22 to 2021-06-01
Event | 2021-03-22: HCP Journeys Project Planning; 2021-03-23: RA Adoption #1; 2021-03-23: CJ principles; 2021-03-24: IBD Adoption #1?; 2021-03-25: IBD onboarding; 2021-03-26: CJ Template #1; 2021-03-29: CJ Journey Kick off; 2021-03-29: RA Adoption #2; 2021-03-30: IDP Adoption #2; 2021-03-31: International CJ iteration #1; 2021-04-01: International CJ iteration #2; 2021-04-06: International RA CJ iteration #1; 2021-04-08: International IBD CJ iteration #1; 2021-04-13: International RA CJ iteration #2; 2021-04-15: International IBD CJ iteration #2; 2021-04-20: France #1; 2021-04-22: France #2; 2021-04-26: France #3; 2021-04-28: Germany #1; 2021-04-30: Germany #2; 2021-05-04: Germany #3; 2021-05-05: UK #1; 2021-05-07: UK #2; 2021-05-11: UK #3; 2021-05-12: Spain #1; 2021-05-14: Italy #1; 2021-05-18: Spain #2; 2021-05-19: Italy #2; 2021-05-21: Spain #3; 2021-05-24: Italy #3; 2021-05-25: NL #1; 2021-05-27: BelLux #1; 2021-05-28: NL #2; 2021-06-01: BelLux #2
Status | 2021-03-22: Complete; 2021-03-23: Complete; 2021-03-23: Complete; 2021-03-24: Open; 2021-03-25: Scheduled; 2021-03-26: Scheduled; 2021-03-29: Open; 2021-03-29: Scheduled; 2021-03-30: Open; 2021-03-31: Scheduled; 2021-04-01: Scheduled; 2021-04-06: open; 2021-04-08: open; 2021-04-13: open; 2021-04-15: open; 2021-04-20: open; 2021-04-22: open; 2021-04-26: open; 2021-04-28: open; 2021-04-30: open; 2021-05-04: open; 2021-05-05: open; 2021-05-07: open; 2021-05-11: open; 2021-05-12: open; 2021-05-14: open; 2021-05-18: open; 2021-05-19: open; 2021-05-21: open; 2021-05-24: open; 2021-05-25: open; 2021-05-27: open; 2021-05-28: open; 2021-06-01: open
Status Indicator | 2021-03-22: Complete; 2021-03-23: Complete; 2021-03-23: Complete; 2021-03-24: Issue; 2021-03-25: On Track; 2021-03-26: On Track; 2021-03-29: At Risk; 2021-03-29: On Track; 2021-03-30: Issue; 2021-03-31: At Risk; 2021-04-01: On Track; 2021-05-11: RA+IBD; 2021-06-01: .
Indication | 2021-03-22: Cross-Indication; 2021-03-23: RA; 2021-03-23: Cross-indication; 2021-03-24: IBD; 2021-03-25: IBD; 2021-03-26: Cross-indication; 2021-03-29: cross-indication; 2021-03-29: RA; 2021-03-30: IBD Core; 2021-03-31: Cross-Indication; 2021-04-01: Cross-Indication; 2021-04-20: RA; 2021-04-22: RA; 2021-04-26: RA; 2021-04-28: RA+IBD; 2021-04-30: RA+IBD; 2021-05-04: RA+IBD; 2021-05-05: RA+IBD; 2021-05-07: RA+IBD; 2021-05-11: UK + core team; 2021-05-12: RA; 2021-05-14: RA; 2021-05-18: RA; 2021-05-19: RA; 2021-05-21: RA; 2021-05-24: RA; 2021-05-25: RA; 2021-05-27: RA; 2021-05-28: RA; 2021-06-01: RA
Attendee Group | 2021-03-22: Core; 2021-03-23: RA Core; 2021-03-23: Core; 2021-03-24: IBD Core; 2021-03-25: IBD Core; 2021-03-26: Core; 2021-03-29: Core + Internaltional; 2021-03-29: RA Core; 2021-03-30: IBD Core; 2021-03-31: Core + international; 2021-04-01: Core + international; 2021-04-06: International Working Group + selected countries; 2021-04-08: International Working Group + selected countries; 2021-04-13: International Working Group + selected countries; 2021-04-15: International Working Group + selected countries; 2021-04-20: France + core team; 2021-04-22: France + core team; 2021-04-26: France + core team; 2021-04-28: Germany + core team; 2021-04-30: Germany + core team; 2021-05-04: Germany + core team; 2021-05-05: UK + core team; 2021-05-07: UK + core team; 2021-05-11: present Internat'l CJ and gather input; 2021-05-12: Spain + core team; 2021-05-14: Italy + core team; 2021-05-18: Spain + core team; 2021-05-19: Italy + core team; 2021-05-21: Spain + core team; 2021-05-24: Italy + core team; 2021-05-25: NL + core team; 2021-05-27: BelLux + core team; 2021-05-28: NL + core team; 2021-06-01: BelLux + core team
Session Goal | 2021-03-22: Formal kickoff for the HCP Journeys project; 2021-03-23: Initiate work on RA adoption ladder; 2021-03-23: agree on design principles and framework; 2021-03-24: Initiate work on IBD adoption ladder; 2021-03-25: On board Patrick and agree on plan; 2021-03-26: first version of CJ template based on agreed principles; 2021-03-29: embark wider international team on project; 2021-03-29: Finalize RA adoption ladder; 2021-03-30: Finalize IBD adoption ladder; 2021-03-31: first working sesssion on CJ to populate with international content; 2021-04-01: second working sesssion on CJ to populate with international content; 2021-04-06: test CJ with selected countries and populate for RA; 2021-04-08: test CJ with selected countries and populate for IBD; 2021-04-13: test CJ with selected countries and populate for RA; 2021-04-15: test CJ with selected countries and populate for IBD; 2021-04-20: present Internat'l CJ and gather input; 2021-04-22: Work on French CJ; 2021-04-26: Finalize France CJ; 2021-04-28: present Internat'l CJ and gather input; 2021-04-30: work on DE CJs; 2021-05-04: work on DE CJs; 2021-05-05: present Internat'l CJ and gather input; 2021-05-07: work on UK CJs; 2021-05-11: Internat'l RA&IBD CJ; 2021-05-12: present Internat'l CJ and gather input; 2021-05-14: present Internat'l CJ and gather input; 2021-05-18: Work on Spain CJ; 2021-05-19: Work on Italy CJ; 2021-05-21: Finalize Spain CJ; 2021-05-24: Finalize Italy CJ; 2021-05-25: present Internat'l CJ and gather input; 2021-05-27: present Internat'l CJ and gather input; 2021-05-28: Finalize Spain CJ; 2021-06-01: Finalize BelLux CJ
Input | 2021-03-23: draft pre populated version based on content received; 2021-03-24: draft pre populated version; 2021-03-25: project presentation; 2021-03-26: principles and framework; 2021-03-29: Presentation deck + outcome of week 1; 2021-03-29: draft version; 2021-03-30: draft version; 2021-03-31: draft template; 2021-04-01: draft template; 2021-04-06: finalized template; 2021-04-08: finalized template; 2021-04-13: finalized template; 2021-04-15: finalized template; 2021-04-20: Internat'l RA CJ; 2021-04-22: Internat'l RA CJ with first add ons; 2021-04-26: Second iteration; 2021-04-28: Internat'l RA&IBD CJ; 2021-04-30: Internat'l RA&IBD CJ with first amendments; 2021-05-04: Internat'l RA&IBD CJ with first amendments; 2021-05-05: Internat'l RA&IBD CJ; 2021-05-07: Internat'l RA&IBD CJ with first amendments; 2021-05-11: parallel session; 2021-05-12: Internat'l RA CJ; 2021-05-14: Internat'l RA CJ; 2021-05-18: Internat'l RA CJ with first add ons; 2021-05-19: Internat'l RA CJ with first add ons; 2021-05-21: Second iteration; 2021-05-24: Second iteration; 2021-05-25: Initial NL CJ; 2021-05-27: Initial BelLux CJ; 2021-05-28: Second iteration; 2021-06-01: Second iteration
Agenda | 2021-03-22: 1) Sharing mobilisation outputs and open items 2) Agreeing joint goals 3) Aligning on project management 4) Workshop Scheduling; 2021-03-23: see deck prepared; 2021-03-23: see deck prepared; 2021-03-24: see deck prepared; 2021-03-25: Presentation deck/ Detail CJ plan; 2021-03-31: parallel session for RA and IBD; 2021-04-01: parallel session for RA and IBD; 2021-04-28: parallel session; 2021-04-30: parallel session; 2021-05-04: parallel session; 2021-05-05: parallel session; 2021-05-07: parallel session; 2021-05-11: first feedback for RA & IBD
Output | 2021-03-23: draft version; 2021-03-23: agreed design principles and framework; 2021-03-24: draft version; 2021-03-25: agree on plan forward incl next meetings; 2021-03-26: first CJ template; 2021-03-29: Finalized version of RA adoption ladder; 2021-03-30: Finalized version of IBD adoption ladder; 2021-03-31: interim version; 2021-04-01: Finalized version of CJ template; 2021-04-06: inputs from countries + amendments; 2021-04-08: inputs from countries + amendments; 2021-04-13: Finalized CJ populated with RA internat'l content; 2021-04-15: Finalized CJ populated with IBD internat'l content; 2021-04-20: first feedback; 2021-04-22: additional feedback; 2021-04-26: Final version for France; 2021-04-28: first feedback for RA & IBD; 2021-04-30: interim version; 2021-05-04: Final version; 2021-05-05: first feedback for RA & IBD; 2021-05-07: interim version; 2021-05-11: Final version; 2021-05-12: first feedback; 2021-05-14: first feedback; 2021-05-18: additional feedback; 2021-05-19: additional feedback; 2021-05-21: Final version for Spain; 2021-05-24: Final version for Italy; 2021-05-25: first feedback; 2021-05-27: first feedback; 2021-05-28: Final version for NL; 2021-06-01: Final version for BelLux
Actual Outcome | bar: 2021-06-01
Notes | 2021-03-24: This will be rescheduling following the initial IBD onoarding on Thursday march 25; 2021-03-29: Likely to be replcaed by individual market sessions fot drive buy-in; 2021-03-30: This will be rescheduling following the initial IBD onoarding on Thursday march 25; 2021-03-31: At risk due to innternational invitees currently undefined; 2021-06-01: .
Attendee 1 | 2021-03-22: Secil; 2021-03-23: Eeva; 2021-03-24: Patrick; 2021-03-25: Elisa; 2021-03-26: Eeva; 2021-03-29: Eeva; 2021-03-30: Patrick; 2021-06-01: .
Attendee 2 | 2021-03-22: Eeva; 2021-03-25: Patrick; 2021-03-29: pre-workshop input from Camille; 2021-06-01: .
Attendee 3 | 2021-03-22: Patrick; 2021-03-29: Pre-workshop input from Elisabeth; 2021-06-01: .
Attendee 4 | 2021-03-22: Johan; 2021-06-01: .
Attendee 5 | bar: 2021-06-01
Attendee 6 | bar: 2021-06-01
Attendee 7 | bar: 2021-06-01
Attendee 8 | bar: 2021-06-01
Attendee 9 | bar: 2021-06-01
Attendee 10 | bar: 2021-06-01
Attendee 11 | bar: 2021-06-01
Attendee 12 | bar: 2021-06-01
Attendee 13 | bar: 2021-06-01
Attendee 14 | bar: 2021-06-01
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.

## Data
Status | Status Indicator | Indication | Attendee Group
Open | On Track | RA | Core
Scheduled | At Risk | IBD | Core + International
Complete | Issue | Cross-Indication | RA Core
| Complete |  | RA Core + International
RA Core + International + Market Rep
RA Market
IBD Core
IBD Core + International
IBD Core + International + Market Rep
IBD Market