## Slide 1: Project Status by Country
Status |  | 
Activity Area | UPDATE / ACTIONS REQUIRED | STATUS
France | 1st Workshop completed Veeva has provided to the French team (1) Workshop 1 deck, (2) Outputs of the Group Exercises, and (3) Draft FR-specific adoption ladder template French Team to (1) provide updates/feedback on the Draft adoption ladder template, and (2) confirm the HCP Journey Structure by Apr 30 Veeva to prepare Workshop 2 Deck & begin draft Custellence journeys following receipt of French updates | 30%
Germany | MOC Meeting completed, German Team has agreed to both RA & IBD journeys Core Team to schedule RA Workshops (starting in May), and IBD Workshops (starting in mid-June) Veeva to prepare Workshop Deck 1 for German session | 5%
UK | MOC Meeting completed, British team confirms value of OC Journeys (RA & IBD) Veeva & Core Team to segment barriers and provide updated adoption ladder to the British Team Core Team to schedule UK Workshop meetings Area of Note – UK team has requested consideration into Adoption Ladder Stage 4 further detail & solution expansion | 5%
Spain | MOC Meeting completed, Spanish team confirms value of OC Journeys Spanish Team noted Workshop 1 should occur late-May Veeva to send above-market adoption ladder templates for reference Veeva to schedule pre-meeting to align on Spanish work performed thus far (segmentation & channel preference work) | 5%
Italy | MOC Meeting completed, Italian team confirms value of OC Journeys Italian team noted Workshop 1 should occur in May, but exact timing to be communicated by Italian team Veeva to send above-market adoption ladder templates for reference Veeva to find Italian-speaking colleague to participate in meetings | 5%
Small Markets (NL & Bellux) | MOC Meetings to be scheduled | 0%
Notes: Would be super helpful to see the current status, timeline and actions for each.
Just to keep us on track, as it's starting to get complicated with the markets in diff places. Just something like 1 swim-lane per market, showing what we need to do, and with stars for the workshops?

## Slide 2: Project Timeline by country
 | April |  |  |  | May | April |  |  |  | June | May |  | 
 | 5th (Week 3) | 12th (4) | 19th (5) | 26th (6) | 3rd (7) | 10th (8) | 17th (9) | 24th (10) | 31st (11) | 7th (12) | 14th (13) | 21st (14) | 28th (15)
France |  |  |  |  |  |  |  |  |  |  |  |  | 
Germany |  |  |  |  |  |  |  |  |  |  |  |  | 
UK |  |  |  |  |  |  |  |  |  |  |  |  | 
Spain |  |  |  |  |  |  |  |  |  |  |  |  | 
Italy |  |  |  |  |  |  |  |  |  |  |  |  | 
Small Markets |  |  |  |  |  |  |  |  |  |  |  |  | 
May 12
RA Workshop 2
May 21
RA Workshop 3
Apr 20
RA Workshop 1
Completed Meeting
Scheduled Meeting
Anticipated Meeting – Not yet in diaries
Apr 13
MOC Meeting
Apr 21
MOC Meeting
Apr 22
MOC Meeting
Apr 22
MOC Meeting
RA Workshop 1
RA Workshop 2
RA Workshop 3
RA Workshop 1
RA Workshop 2
RA Workshop 3
RA Workshop 1
RA Workshop 2
RA Workshop 3
IBD Workshop 1
IBD Workshop 2
IBD Workshop 3
RA Workshop 1
RA Workshop 2
RA Workshop 3
UK IBD Meetings to occur in Sept’21
MOC Meeting NL
MOC Meeting Bellux