## Slide 1: Workstream Plan
April | April |  |  | May | May |  | 
5th (3) | 12th (4) | 19th (5) | 26th (6) | 3rd (7) | 10th (8) | 17th (9) | 24th (10)
Scope & Deliverables Definition
CRM
Johan/Boris
Adoption Journey Alignment
Adoption Journey Field Alignment Meeting
60mins
Ladder <-> CRM
Mapping the existing CRM fields with the Adoption Ladder
Identifying whether additional fields could be added to CRM to better represent the journeys
CRM Field Requirements
Requirements sign-off for next sprint
30 mins
Journey Visualisations & Measurement
CRM field alignment review
30 mins
Deliverable 1: Sprint Requirements
Deliverable 2: Simple guide to demonstrate how the Adoption Ladders and CRM will be aligned
Deliverable 3: Outline of the data & analysis quick wins approach for measuring Journey/Ladder execution
Deliverable 4: Overview of the ‘next steps’ for operationalising/visualising Journeys – such as a MyInsights dashboard
Journey Visualisation
Journey Measurement
Ideation Session
60-90 mins
Approach review
45 mins
Ideation Session
60-90 mins
Approach review
45 mins
CRM/Adoption Field Alignment Implementation
CDP
TBC with Saad